ECN MODERNISATION STRATEGY

Replacing Stargile with a Modern, AI-Ready

Engineering Change Note System

| Version | 2.0 |
| --- | --- |
| Status | Draft for Management Review |
| Programme | Engineering / IT Modernisation |
| Related Doc | MES Modernisation Strategy v3.0 |
| Changes | v2.0 closes all gaps from v1.0 gap analysis — see Executive Summary |

# Executive Summary

The Engineering Change Note (ECN) system is a production-critical workflow used by production engineers to plan, approve, and execute changes to Bills of Materials (BOMs), routes, and item master records within the Movex/M3 ERP system. Currently delivered by a third-party product called Stargile, this system sits at the intersection of ISO 13485 medical device manufacturing compliance, ERP data integrity, and multi-disciplinary engineering coordination.

This document presents a structured, four-phase strategy to replace Stargile with a custom-built, modern ECN platform. Unlike a typical legacy modernisation, this project begins from a position of significant advantage: full source code access, available subject matter experts, an existing M3 API integration layer, a mandated retirement from the system owner, and strong user pull driven by frustration with the current system.

The recommended approach is a clean build on a modern, loosely-coupled stack — Python/FastAPI backend, PostgreSQL, React/TypeScript frontend — designed from day one as a foundation component of the Organisational AI Platform. The project is structured in four phases across approximately 20 weeks, with each phase gated by a documented deliverable before the next begins.

Three architectural decisions underpin the long-term value of this project: an abstract ERP Adapter pattern that insulates ECN logic from the Movex-to-IFS migration; an event bus that exposes ECN state changes to IoT and AI systems; and an immutable audit trail designed to satisfy ISO 13485 requirements from day one.

Strategic Note This ECN replacement is not just a system upgrade. It is the first delivered component of the Organisational AI Platform — establishing the architectural patterns, integration contracts, and data foundations that every subsequent system modernisation will inherit.

STRATEGIC RECOMMENDATION: Full clean build on Python/FastAPI, deployed on-premises on Windows Server via IIS + NSSM, using Stargile and SME knowledge as the living specification — not as a foundation to extend.

# 1. Current Situation Analysis

## 1.1 The Problem in Plain Terms

- Large portions of Stargile are unused — creating confusion for new engineers

- Workflow does not match how teams work — confirmed source of personnel friction and rotation

- Movex integration is brittle — Status 50 failures and date-conflict workarounds are part of regular procedure, not edge cases

- Cannot participate in AI or IoT initiatives — no event stream, no API surface, no structured audit data

- Architecture cannot survive the Movex → IFS migration — the coupling is baked in

## 1.2 Advantages Over a Typical Legacy Project

| Factor | MES Project | ECN Project |
| --- | --- | --- |
| Source code access | No (LabVIEW) | Yes — full, runnable |
| SME availability | Reluctant, at risk | Available and willing |
| M3 integration | Unknown at start | Working API layer exists |
| Management mandate | Required via strategy | Already in place |
| Users pull factor | Unknown | Confirmed — engineer frustration |
| Compliance context | General | ISO 13485 understood |

## 1.3 What Phase 1 Must Still Confirm

- Full ECN state machine including Status 60 → Completed exit (critical gap — see Section 4.4)

- Every Movex M3 call: item, BOM, route, errors, retry

- Current and complete role model

- Formal unused functionality list

- Excel template: retain as-is, replace, or augment (Phase 1 Track B, SME sign-off)

- SMT programmes: location, ownership, update procedure (dedicated Phase 1 SMT session)

- Historical data retention decision: how Stargile records are preserved post-decommission

## 1.4 Regulatory Context: ISO 13485

Every BOM or route change must be traceable to an ECN with an immutable record of who initiated it, who approved it, and when. Software Validation (IQ/OQ/PQ) is required before go-live. Records must be retained for the device lifetime plus the applicable jurisdiction period.

# 2. Strategic Options Assessment

| Criterion | A: Do Nothing | B: Incremental | C: Clean Build | D: Commercial |
| --- | --- | --- | --- | --- |
| Removes Movex coupling | No | No | Yes | Partial |
| Supports IFS migration | No | No | Yes | Vendor-dependent |
| Enables AI / IoT | No | Partial | Yes | Partial |
| Retires dead functionality | No | Partial | Yes | N/A |
| ISO 13485 compliance | Maintained | Maintained | Improved | Config-dependent |
| Builds Org AI Platform | No | No | Yes | No |
| Risk level | High | Medium | Low–Medium | Medium–High |
| Recommendation | ✗ | ✗ | ✓ | ✗ |

Option C — Full Custom Build — is recommended. See Appendix C for the full Architectural Decision Log, including the justified deviation from the existing .NET workspace standard.

# 3. Recommended Strategy: Four-Phase Programme

| Phase | Weeks | Key Gate Deliverables |
| --- | --- | --- |
| Phase 1 — Discovery | 1–3 | Behavioural Spec + ERP Adapter Interface + Retired Functionality List + Excel decision + SMT session + Retention decision (QA signed) |
| Phase 2 — Architecture | 4–5 | ADR + Data Model + NFR baseline + Infra confirmed + Movex sandbox confirmed + Build Plan |
| Phase 3 — Build | 6–17 | Working system + IFS adapter stub + Signed UAT report + Training materials |
| Phase 4 — Cutover | 18–20 | Go-live + Software Validation (IQ/OQ/PQ) + Training records + Rollback procedure rehearsed + Stargile decommissioned |

PHASE 1 — Discovery, Behavioural Specification and ERP Contract Weeks 1–3

### Track A — Source Code Analysis

- Map the complete ECN state machine — specifically resolve the Status 60 exit mechanism (see Section 4.4)

- Extract every Movex M3 API call: method, payload, response, error conditions, retry behaviour

- Identify the background process that triggers deferred Movex updates (flagged uncertain in April 2018 transcript)

- Map the complete data model and all entity relationships

### Track B — SME Behavioural Sessions

- Confirm current role model, all exception paths, all edge cases

- Excel template decision: retain as-is, replace with native UI form, or augment — must be signed off by Production Engineer

- Dedicated SMT Engineer session: where do SMT programmes physically reside? What update action is required when SMT-affecting ECN is approved? How does the ECN system record that the update occurred? (see Section 7.7)

- Confirm and sign off unused functionality list

### Track C — ERP Adapter Interface Definition

Define the abstract interface between ECN business logic and any ERP. Add validate_payload method to pre-check effective date conflicts before Movex submission. See Section 7.2.

### Historical Data Retention Decision (Phase 1 Gate — QA sign-off required)

| Option | Description | Recommendation |
| --- | --- | --- |
| 1 — Migrate to new DB (recommended) | All Stargile ECN records migrated with archived = true flag. Single searchable system. | ✓ Recommended |
| 2 — PDF export + archive DB | Each completed ECN exported as signed PDF. Stargile DB preserved read-only. | Acceptable |
| 3 — Read-only Stargile instance | Stargile kept running in read-only mode. Highest operational cost. | ✗ Not recommended |

| Phase 1 Gate Deliverables — all must be complete and signed off before Phase 2 begins |  |  |
| --- | --- | --- |
| Deliverable | Owner | Sign-off Required |
| Behavioural Specification (incl. full state machine) | Developer + SMEs | Production Engineer, Document Control |
| ERP Adapter Interface | Developer | IT / Architecture review |
| Retired Functionality List | Developer + SMEs | Manager, Production Engineer |
| Excel template decision | SMEs | Production Engineer |
| SMT session findings | Developer + SMT Engineer | SMT Engineer |
| Historical data retention decision | Developer + QA | QA sign-off |

PHASE 2 — Architecture Decision, Data Model and Build Plan Weeks 4–5

| Phase 2 Gate Conditions — ALL must be met before Phase 3 begins |  |  |
| --- | --- | --- |
| Gate Condition | Owner | If Not Met |
| Architecture Decision Record complete | Developer | Extend Phase 2 |
| Non-functional requirements baselined | Developer + IT | Extend Phase 2 |
| Movex test/sandbox environment confirmed Company 300 | IT | Phase 3 cannot begin — escalate to management |
| Infrastructure provisioned or confirmed | IT | Phase 3 cannot begin — escalate |
| Contractor/resource confirmed (if needed) | Manager | Phase 3 cannot begin — escalate |
| Historical retention decision signed by QA | QA | Phase 3 cannot begin |

PHASE 3 — Build, Parallel Operation and Validation Weeks 6–17

### Parallel Operation Protocol

- From cutover date: all new ECNs created in the new system

- All open Stargile ECNs completed in Stargile — no ECN exists in both systems simultaneously

- This is ISO 13485-compliant and risk-free from a traceability perspective

### Build Sequence

| Sprint | Weeks | Deliverables |
| --- | --- | --- |
| Sprint 1 | 6–8 | Scaffolding, Docker/NSSM on Windows, IIS setup, authentication (AD integration if available), role model, ECN creation, basic UI |
| Sprint 2 | 9–11 | Item upload (Excel template support), BOM management with optimistic locking + conflict resolution UI, route management |
| Sprint 3 | 12–14 | Approval routing engine, notification system (SMTP + WebSocket), ERP Adapter Movex M3 implementation with validate_payload, Status 50 error recovery |
| Sprint 4 | 15–17 | Audit log with hash chain, compliance reporting, IFS adapter stub (feature-flagged), parallel operation tooling, end-to-end testing, UAT, training materials |

Sprint 4 explicit deliverable: IFS Adapter Stub — implements ERPAdapter interface with all methods raising NotImplementedError. Deployed behind feature flag. Validates that the interface contract is complete before IFS work begins.

PHASE 4 — Cutover, Compliance Validation and Handover Weeks 18–20

### Cutover Protocol

- Confirm all open Stargile ECNs at terminal state — if any remain, extend parallel operation. Do not cut over with open ECNs.

- Engineer communications: all users notified at least two weeks in advance. Training sessions completed and attendance recorded.

- Go-live: new system live for new ECNs. Stargile set to read-only.

- 72-hour care window: both systems monitored, dedicated support channel active.

- 30-day rollback window: Stargile accessible read-only for reference.

- After 30 days: execute historical data migration, archive Stargile, decommission.

### Operational Rollback Procedure

Rollback Criteria — initiate if any of the following occur within the 72-hour care window

- Data loss: any ECN record created in the new system cannot be retrieved or is corrupted

- Compliance breach: audit trail fails to record an action, or approval records are incomplete

- ERP push failure rate exceeds 20% of attempted ECNs with no clear resolution path

- Blocker defect: prevents engineers from completing a business-critical ECN workflow

Step-by-Step Rollback

| Step | Timing | Action | Owner |
| --- | --- | --- | --- |
| 1 — Decision | Hour 0 | Project lead and manager confirm rollback in writing (email/Teams) | Project Lead + Manager |
| 2 — Stargile reactivation | Hour 0–1 | IT removes read-only restriction. Confirm write access restored. | IT |
| 3 — User communication | Hour 1 | Email to all engineers: use Stargile until further notice | Project Lead |
| 4 — In-flight ECNs | Hour 1–4 | For each ECN created in new system: if not pushed to Movex, recreate in Stargile. If pushed successfully, add retrospective Stargile entry. QA to review each case. | Developer + QA |
| 5 — Root cause analysis | Day 1–3 | Identify and fix root cause. Do not reschedule until fix is confirmed and regression tested. | Developer |
| 6 — Reschedule | Day 3+ | Communicate revised go-live date once fix is confirmed | Project Lead |

The rollback procedure document is a Phase 4 pre-cutover deliverable. It must be rehearsed in a tabletop exercise with IT and the engineering team before go-live.

### Software Validation Documentation (ISO 13485)

| Document | Content | Evidence Source |
| --- | --- | --- |
| Installation Qualification (IQ) | System installed and configured correctly in production | Deployment runbook execution log |
| Operational Qualification (OQ) | System performs as specified under normal and abnormal conditions | Behavioural Spec + UAT Report |
| Performance Qualification (PQ) | System performs correctly in production with real data | Pilot period monitoring data |

### User Training — ISO 13485 Requirements

| Session | Audience | Timing | Duration |
| --- | --- | --- | --- |
| Production Engineer training | All Production Engineers | 2 weeks before go-live | 2 hours |
| Approver training | Document Control, SMT, Test Engineers | 2 weeks before go-live | 1 hour |
| Administrator training | IT + designated admin | 3 weeks before go-live | 2 hours |
| Train-the-trainer | 1 Production Engineer + 1 QA person | 3 weeks before go-live | 3 hours |

Training records — attendance records signed by attendee and trainer — are retained as quality records for the duration of the system's operational life plus the ISO 13485-required retention period.

# 4. Non-Functional Requirements

Non-functional requirements define how well the system must perform — not what it does. These must be baselined in Phase 2 and used as acceptance criteria for Phase 3 testing. They form part of the ISO 13485 Software Validation evidence.

## 4.1 Performance

| Requirement | Target | Rationale |
| --- | --- | --- |
| Page load time (initial) | < 3 seconds on local network | Engineering workstation standard |
| API response (standard operations) | < 500ms at 95th percentile | Workflow productivity |
| API response (ERP push) | < 30 seconds (Movex SLA-dependent) | User expectation for ERP operations |
| Concurrent users | 20 simultaneous without degradation | Peak engineering shift estimate |
| BOM load (> 200 lines) | < 5 seconds | Complex product BOMs |
| Audit log query (12 months data) | < 10 seconds | ISO 13485 compliance review |

## 4.2 Availability and Reliability

| Requirement | Target | Rationale |
| --- | --- | --- |
| Uptime (production) | 99% during business hours Mon–Fri 07:00–18:00 | Engineering shift coverage |
| Planned downtime window | Off shift (weekends, overnight) | Minimise production impact |
| Recovery Time Objective (RTO) | 4 hours | Engineers have workaround for up to 4 hours |
| Recovery Point Objective (RPO) | Maximum 1 hour data loss | Hourly transaction log backups |
| Data integrity | Zero tolerance for silent data loss | ISO 13485 requirement |

## 4.3 Scalability

| Requirement | Target | Notes |
| --- | --- | --- |
| User growth | 100 users without architectural change | 5-year headroom |
| ECN record volume | 10,000 ECNs without performance degradation | Long-term archive growth |
| BOM line volume | BOMs with up to 500 components | Complex assemblies |
| Event throughput | 100 events per minute sustained | Peak approval activity |

## 4.4 Maintainability

- All code in Git with meaningful commit messages from day one

- Code coverage: 80% minimum for backend business logic

- All API endpoints documented in OpenAPI specification (auto-generated by Fast API)

- Database schema changes via migration scripts only — no manual modifications

- Environment configuration via environment variables — no hardcoded values

- Deployment repeatable from a single command

- Runbook for all operational procedures: start, stop, backup, restore, user management

## 4.5 Usability

- Usable on standard engineering workstations (Windows 10/11, Chrome or Edge)

- No browser plugins or special client-side software required

- Forms validate client-side with clear, actionable error messages

- All ECN status transitions are visible and understandable without memorising status codes

- Clear view of what action is required from each user at each stage

## 4.6 Compliance

- Every user action that changes data is recorded in audit log with identity and timestamp

- Password confirmation required for approval actions — non-repudiation

- Audit log records are immutable — no update or delete permitted

- Deletion of ECN records is prevented — only status transitions to archived or superseded

- System configuration changes (role assignments, settings) are audit-logged

# 5. Infrastructure and Hosting

Deployment model: on-premises, Windows Server. No cloud hosting. No external SaaS dependencies for core functionality. Driven by organisational policy, data sensitivity, ISO 13485 auditability, and internal network ERP connectivity.

## 5.1 Server Architecture

| Server | Role | Minimum Spec |
| --- | --- | --- |
| App Server | Python/FastAPI via NSSM, Redis/WSL2, IIS reverse proxy | Windows Server 2019+, 8 cores, 16 GB RAM, 100 GB SSD |
| DB Server | PostgreSQL 16 | Windows Server 2019+, 4 cores, 16 GB RAM, 500 GB SSD |
| Staging Server | Mirror of production for testing and UAT | Same spec as production — separate hardware before go-live |

Single-server deployment (all services on one machine, 16 cores / 32 GB RAM minimum) is acceptable for the initial pilot phase but must be separated before production go-live.

## 5.2 Technology Stack on Windows Server

| Component | Technology | Windows Deployment Method |
| --- | --- | --- |
| FastAPI application | Python 3.12 + uvicorn | NSSM (Non-Sucking Service Manager) wraps uvicorn as a Windows Service with auto-restart |
| Web server / reverse proxy | IIS | IIS serves React static build; proxies /api/* to uvicorn on localhost:8000 |
| Database | PostgreSQL 16 | EnterpriseDB installer for Windows; data on dedicated SSD |
| Event bus | Redis Streams | Redis via WSL2 on Windows Server 2019+; fallback: PostgreSQL LISTEN/NOTIFY |
| Frontend | React 18 + TypeScript build | Static files served by IIS; no Node.js runtime required in production |
| TLS certificate | Internal CA (ADCS) | Issued from Active Directory Certificate Services; workstations already trust internal CA |

## 5.3 Network Topology

| Internal network only — no internet-facing endpoints |  |  |
| --- | --- | --- |
| Connection | Protocol | Notes |
| Workstation → IIS (App Server) | HTTPS port 443 | TLS certificate from internal ADCS |
| IIS → FastAPI (uvicorn) | HTTP localhost:8000 | Loopback only — not exposed externally |
| FastAPI → PostgreSQL | TCP internal network port 5432 | Restricted to App Server IP in pg_hba.conf |
| FastAPI → Redis (WSL2) | TCP localhost:6379 | Loopback only |
| FastAPI → Movex M3 API | Existing integration (internal network) | Uses existing working M3 API layer |

## 5.4 Backup and Recovery

| Backup Type | Schedule | Retention | Tool |
| --- | --- | --- | --- |
| PostgreSQL full backup | Nightly at 01:00 | 30 days | pg_dump + Windows Task Scheduler |
| PostgreSQL WAL (transaction log) | Continuous / hourly archive | 7 days | PostgreSQL WAL archiving |
| Application code | Continuous | Git history | Git repository |
| Environment config | On every change | Git history | Git (secrets excluded — .env.example only) |
| Windows Server system state | Weekly | 4 weeks | Windows Server Backup |

Recovery procedure must be documented and tested before go-live. A successful recovery from backup must be demonstrated in the staging environment as part of the IQ (Installation Qualification) evidence.

## 5.5 Environments

| Environment | Purpose | Movex Connection |
| --- | --- | --- |
| Development | Developer local machines | Mocked M3 responses or sandbox |
| Staging / Test | Phase 3 testing, UAT, regression | Movex Company 300 — MANDATORY (Phase 2 gate) |
| Production | Live system | Movex Company 100 |

# 6. Notification System Design

Recommendation: Exchange SMTP (email) as the primary durable notification channel + WebSocket for real-time in-app notifications. No SaaS dependency. No Microsoft Teams requirement. Fully on-premises and ISO 13485-auditable.

## 6.1 Architecture

| Channel | Technology | Durability | When Used |
| --- | --- | --- | --- |
| Email (primary) | SMTP via existing Exchange Server / M365 | Durable — delivery traceable | All notifications — durable record of delivery |
| In-app real-time (secondary) | WebSocket (Fast API native) | Ephemeral — browser must be open | When engineer is actively using the system |
| System events | Windows Application Event Log | Persistent — integrates with Windows monitoring | Application errors, service start/stop, DB failures |

## 6.2 Notification Event Matrix

| Trigger Event | Recipient | Channel | Content |
| --- | --- | --- | --- |
| ECN submitted for approval | All required approvers | Email + In-App | ECN number, title, link, required action |
| Approver signs off | ECN creator | Email + In-App | Who approved, status |
| Approver rejects | ECN creator | Email + In-App | Who rejected, rejection reason |
| All approvals received | Creator, Document Control | Email + In-App | ECN moving to ERP push |
| ERP push failed (Status 50 error) | Creator, Document Control | Email + In-App | Error message, link to error log, required action |
| ERP push succeeded (Status 60) | ECN creator | In-App | Confirmation |
| ECN approaching stale (no action X days) | Creator, pending approver | Email | Reminder with link |

## 6.3 Configuration

- Email templates stored as Jinja2 files — changeable without code deployment

- SMTP host, port, sender address, and credentials stored as environment variables — never in Git

- Staleness reminder threshold configurable (default: 5 business days)

- Each notification delivery is recorded in the Notification table (ecn_id, recipient, channel, event_type, sent_at, status) for audit purposes

# 7. Technical Architecture

## 7.1 Recommended Tech Stack

| Layer | Technology | Rationale |
| --- | --- | --- |
| Backend API | Python 3.12 + Fast API | AI agent integration, OpenAPI auto-generation, async-native. See Appendix C for deviation from .NET standard. |
| Database | PostgreSQL 16 | ISO 13485 compliance, JSONB BOM flexibility, SQL accessible by AI agents |
| Frontend | React 18 + TypeScript | Team capability, form-heavy workflow UI |
| Event Bus | Redis Streams (WSL2) / PostgreSQL fallback | ECN state events for IoT/AI subscribers — see Section 5.2 |
| Notifications | SMTP (Exchange) + WebSocket | On-premises Windows-compatible, no SaaS dependency |
| Auth | JWT + RBAC (+ AD integration) | ISO 13485 non-repudiation; AD integration eliminates separate password management |
| Web Server | IIS (reverse proxy) | Windows Server standard — see Section 5.2 |
| App Host | Uvicorn + NSSM Windows Service | Production-grade Python hosting on Windows |
| ERP Integration | ERP Adapter pattern | Movex today, IFS tomorrow |

## 7.2 The ERP Adapter Pattern

The single most important architectural decision in the project. The ECN application never calls Movex directly — it calls the adapter. When IFS arrives, a new adapter is written. The ECN application is unchanged.

| Method | Purpose | Notes |
| --- | --- | --- |
| push_item(item) | Create or update an item record |  |
| push_bom(bom) | Create or update a bill of materials |  |
| push_route(route) | Create or update a manufacturing route |  |
| get_errors(ecn_id) | Retrieve errors from last push attempt |  |
| retry_push(ecn_id) | Retry a failed push operation |  |
| validate_payload(payload) | Pre-validate payload before ERP submission | NEW in v2.0 — catches date-conflict errors before Status 50 |

| Adapter | Status | Production Active? |
| --- | --- | --- |
| MovexM3Adapter | Built in Phase 3 Sprint 3 | Yes |
| IFSAdapter (stub) | Built in Phase 3 Sprint 4 | No — feature-flagged off |

## 7.3 BOM Concurrency Design

### Problem

Two engineers open and edit the same BOM simultaneously. Without concurrency control, the second save silently overwrites the first. Under ISO 13485, this is a compliance risk as much as a data integrity risk.

### Solution: Optimistic Locking with Conflict Resolution UI

Every BOM and BOMLine record carries a version integer column. The save sequence:

| Step | What Happens |
| --- | --- |
| 1. Engineer A opens BOM | API response includes: {bom_id: 42, version: 7, ...} |
| 2. Engineer B opens same BOM | Also receives version: 7 |
| 3. Engineer A saves | API call includes version: 7. DB version is 7 — match. Update succeeds. Version becomes 8. |
| 4. Engineer B saves | API call includes version: 7. DB version is 8 — mismatch. API returns HTTP 409 Conflict with diff payload. |
| 5. Conflict resolution UI | Engineer B sees: 'Your changes' vs 'Current saved version'. Options: merge, discard, or overwrite (requires explicit confirmation + audit log entry). |

### Additional Safeguards

- 'Last edited by [name] at [timestamp]' displayed on every BOM open — visibility before editing begins

- For BOMs on active ECNs (Approved, ERP Pending): soft edit lock warning modal before editing

- Override with explicit confirmation is recorded as an audit log entry — compliance trail maintained

### Data Model Addition

| Column | Type | Purpose |
| --- | --- | --- |
| version | INTEGER NOT NULL DEFAULT 1 | Incremented atomically on every successful update |
| last_edited_by | INTEGER REFERENCES users(id) | Displayed in UI — who last modified |
| last_edited_at | TIMESTAMP WITH TIME ZONE | Displayed in UI — when last modified |

## 7.4 ECN State Machine (v2.0 — with Status 60 Resolution)

Critical gap from v1.0: the April 2018 transcript does not show an explicit terminal state after Status 60. Phase 1 Track A must resolve this from Stargile source. The v2.0 design adds an explicit Completed state (code 70) that Status 60 transitions into once notifications are sent. If Phase 1 confirms Status 60 is already terminal, collapse Status 60 and completed into one.

| State | Code | Description | Exit Condition |
| --- | --- | --- | --- |
| Draft | 10 | Created, not yet submitted | Engineer submits |
| Submitted | 20 | Routed to approvers | First approver acts |
| Under Review | 30 | Approvals in progress | All required approvals received |
| Approved | 40 | All approvals received | ERP push initiated |
| ERP Pending | 50 | Submitted to Movex M3, awaiting confirmation | Push result received |
| ERP Failed | 55 | Movex returned an error | Engineer enters error recovery |
| Error Recovery | 57 | Engineer correcting payload | Retry submitted |
| ERP Success | 60 | Movex confirmed the update | Post-push notifications sent |
| Completed | 70 | Explicit terminal state — ISO 13485 endpoint | None — record immutable |
| Rejected | 90 | Approver rejected — terminal | None — record immutable |

## 7.5 Data Model

| Entity | Key Fields | Purpose |
| --- | --- | --- |
| ECN | id, title, customer_ref, status, effective_date, created_by, created_at | Master ECN record |
| ECNItem | ecn_id, item_number, is_new, description | Items created/modified |
| BOM | id, bom_number, revision, effective_date, version, last_edited_by, last_edited_at | BOM header with concurrency version |
| BOMLine | bom_id, component, quantity, from_date, version | BOM components with concurrency version |
| Route | id, product_id, revision, version | Manufacturing route |
| RouteOperation | route_id, operation, description, sequence | Route steps |
| ApprovalRole | ecn_id, role, required, assigned_to | Roles required for this ECN |
| ApprovalRecord | ecn_id, role, user_id, decision, timestamp, password_confirmed | Immutable approval entries |
| ERPSyncRecord | ecn_id, attempt, payload, response, status, error, retried_at | Every ERP push attempt |
| AuditLog | entity, entity_id, action, user_id, timestamp, before_state, after_state, row_hash | Append-only — hash chain for tamper detection |
| Notification | ecn_id, recipient_id, channel, event_type, sent_at, status | Notification delivery record |

## 7.6 Role Model

| Role | Responsibility | Required? | Can Create? | Can Approve? |
| --- | --- | --- | --- | --- |
| Production Engineer | Creates and owns the ECN | Yes (creator) | Yes | No |
| Document Control / QA | Mandatory approver | Yes — always | No | Yes |
| SMT Engineer | Approves if SMT components affected | Conditional | No | Yes |
| Test Engineer | Approves if firmware/test procedure affected | Conditional | No | Yes |
| Validation Engineer | Required for medical device customer ECNs | Conditional | No | Yes |
| Administrator | User and system management | System role | Config only | No |

## 7.7 SMT Programmes — Integration Boundary

SMT machine programmes (Gerber files, pick-and-place files) are NOT managed within the ECN system. They reside on SMT machine controllers or a shared engineering file server, owned by the SMT engineering team.

| Boundary | In ECN System | Outside ECN System |
| --- | --- | --- |
| SMT programme files | No — not stored or uploaded | Yes — on SMT machine controllers / file server |
| SMT programme updates | No — not performed | Yes — SMT Engineer updates on their own systems |
| SMT approval record | Yes — immutable ApprovalRecord with timestamp | No |
| SMT update confirmation | Yes — SMT Engineer's approval action IS the confirmation | No |
| Notification to SMT Engineer | Yes — email + in-app when SMT-affecting ECN submitted | No |

Phase 1 Track B deliverable: the SMT Engineer SME session must confirm this design is accurate and must document exactly what 'SMT programmes updated' means operationally — which files, on which systems, verified how.

# 8. Security Design

## 8.1 Threat Model

The ECN system operates on a closed internal network. Primary threat vectors:

| Threat | Vector | Mitigation |
| --- | --- | --- |
| Insider — unauthorised record modification | Internal user | RBAC, immutable audit log, password confirmation for approvals |
| Privilege escalation | Low-privilege user gains approval rights | RBAC enforced at API level, not only UI; role changes audit-logged |
| Audit trail tampering | Database access or SQL injection | Append-only permissions, hash chain integrity, parameterised queries |
| BOM IP theft | Unauthorised data export | RBAC restricts export; no export without Document Control role |
| Session hijacking | Stolen JWT token | HTTP-only cookies, IP+UA binding, server-side revocation |
| Injection attacks | Form inputs, file uploads | Pydantic validation, parameterised SQL (SQLAlchemy ORM), file type/size validation |

## 8.2 Authentication

| Token Type | Lifetime | Storage | Purpose |
| --- | --- | --- | --- |
| Access token | 15 minutes | HTTP-only cookie | API authorisation — short-lived to limit exposure |
| Refresh token | 8 hours (one shift) | HTTP-only cookie + server revocation list | Session continuation without re-login during shift |

### Password Policy

- Minimum 10 characters — upper, lower, digit, and special character required

- Maximum 90-day expiry with change enforcement

- Password history: last 10 passwords cannot be reused

- Account lockout after 5 failed attempts — unlocked by Administrator only

- Approval actions require password re-confirmation at point of action (ISO 13485 non-repudiation)

Active Directory integration is recommended. Engineers log in with Windows credentials. Password policy inherited from AD Group Policy. Leavers are automatically locked out when AD account is disabled — no manual de-provisioning required.

## 8.3 Authorisation — RBAC Matrix

| Permission | Prod. Engineer | Doc. Control | SMT Engineer | Test Engineer | Administrator |
| --- | --- | --- | --- | --- | --- |
| Create ECN | ✓ | — | — | — | — |
| Edit own draft ECN | ✓ | — | — | — | — |
| Edit others' draft ECN | — | — | — | — | ✓ |
| Submit for approval | ✓ | — | — | — | — |
| Approve ECN (own role) | — | ✓ | ✓ | ✓ | — |
| View all ECNs | ✓ | ✓ | ✓ | ✓ | ✓ |
| View audit log | — | ✓ | — | — | ✓ |
| Manage users / roles | — | — | — | — | ✓ |
| Trigger ERP retry | ✓ | ✓ | — | — | ✓ |
| Export compliance report | — | ✓ | — | — | ✓ |

## 8.4 Transport Security

- All traffic over HTTPS — TLS 1.2 minimum, TLS 1.3 preferred

- HSTS header enforced (Strict-Transport-Security)

- IIS configured to redirect all HTTP requests to HTTPS

- Certificate issued by internal CA (ADCS) — self-signed not permitted in production

- Internal API-to-database and API-to-Redis connections on localhost — no TLS required for loopback

## 8.5 Data Security

| Data Type | Classification | Protection |
| --- | --- | --- |
| BOM component details | Confidential — IP | RBAC access control; no export without authorisation |
| ECN approval records | Quality record — ISO 13485 | Immutable, audit-logged, backup mandatory |
| User passwords | Sensitive | Bcrypt hashed with salt — never stored in plaintext |
| ERP API credentials | Secret | Windows Credential Manager or environment variables — never in Git |
| Audit log | Quality record | Append-only table; no UPDATE/DELETE permissions at DB level |

Encryption at rest: PostgreSQL data directory on an encrypted BitLocker volume. Protects against physical media theft.

## 8.6 Audit Trail Security (ISO 13485)

### Immutability at Database Level

-- Application DB user has INSERT + SELECT on audit_log only

REVOKE UPDATE, DELETE ON audit_log FROM ecn_app_user;

Update and delete are impossible at the database permission level — not just enforced in application code.

### Tamper Detection — Hash Chain

Each audit log row carries a SHA-256 hash of its content fields plus the hash of the previous row. Any modification to a row breaks the chain and is detectable by a validation query. This query is run as part of the daily backup verification.

## 8.7 Input Validation and Injection Prevention

- All database queries use parameterised statements (SQLAlchemy ORM) — raw string concatenation in queries is prohibited

- All user inputs validated server-side using Pydantic models — FastAPI's native validation library

- File uploads (Excel templates) validated for type, size (max 10 MB), and content structure before processing

- React rendering escapes HTML output — no dangerouslySetInnerHTML without security review

- Every API endpoint validates requesting user role before processing any action

## 8.8 Session Management

- Sessions bound to user's IP address and user-agent string at login — significant change invalidates session

- Server-side refresh token revocation list in Redis — logout immediately invalidates token

- Maximum 3 concurrent sessions per user — protects against shared credential usage

## 8.9 Pre-Go-Live Security Checks

- OWASP Top 10 review against codebase and deployment configuration

- Dependency vulnerability scan (pip audit for Python, npm audit for frontend) — zero high-severity at go-live

- Authentication bypass testing: all API endpoints return 401 for unauthenticated requests

- Authorisation boundary testing: RBAC enforced at API level confirmed

- Audit log integrity check: hash chain valid on test environment data

# 9. AI and Organisational Platform Integration

## 9.1 How the ECN System Enables AI Capabilities

| ECN Capability | AI Capability Unlocked |
| --- | --- |
| Structured ECN event stream | AI agents respond to manufacturing changes in real time |
| BOM version history in PostgreSQL | ML models learn patterns in engineering changes |
| Approval audit log | AI identifies bottlenecks and predicts approval delays |
| ERP push history with error records | AI predicts Movex/IFS conflicts before submission |
| OpenAPI specification | Agents discover and call ECN functions using standard tool-use patterns |
| ISO 13485 audit data | Compliance AI monitors and flags deviations automatically |

## 9.2 Agent Hooks to Build From Day One

- OpenAPI specification — auto-generated by FastAPI; becomes the agent's tool definition

- validate_bom endpoint — accepts a proposed BOM, returns rule-check results (rule-based initially, ML later)

- Event bus subscriptions — agents subscribe without modifying the ECN system

- Structured audit log — queryable by agents for compliance monitoring

- /health and /metrics endpoints — standard platform observability hooks

# 10. Change Management

Change management risk for this project is LOW. Management has mandated the replacement. User frustration is the confirmed driver. The critical actions are involving engineers in Phase 1 Track B so they feel ownership, and delivering training before cutover.

## 10.1 Stakeholder Map

| Stakeholder | Role | Interest | Engagement |
| --- | --- | --- | --- |
| Manager / Sponsor | Decision owner | Successful delivery, reduced frustration | Phase gate reviews, bi-weekly updates |
| Production Engineers | Primary users | System that makes their job easier | Track B SME sessions, UAT participation |
| Document Control / QA | Approvers + compliance | Audit trail quality, ISO 13485 | SME sessions, UAT sign-off |
| SMT / Test Engineers | Conditional approvers | Simple, clear approval interface | SMT session (Track B), UAT |
| IT | Infrastructure + security | Maintainable, supportable system | Architecture Phase 2, server provisioning |

## 10.2 Communication Cadence

| Touchpoint | Audience | Frequency | Content |
| --- | --- | --- | --- |
| Steering update | Manager / Sponsor | Every 2 weeks | Progress vs plan, risks, decisions needed |
| Phase gate review | Manager + key stakeholders | End of each phase | Gate deliverable presentation, go/no-go |
| Engineer briefing | All ECN users | Phase 1 kickoff, Phase 3 start, pre-cutover | What is being built and how they will be involved |
| Project log | All stakeholders | Weekly | 1-page status: done, doing, blocked, next |

# 11. Risk Register

| Risk | Impact | Likelihood | Mitigation |
| --- | --- | --- | --- |
| Historical data lost at Stargile decommission | Critical | Certain without action | Phase 1 gate: QA-signed retention decision. Recommended: migrate all records to new DB with archived flag before decommissioning. |
| Status 60 exit mechanism undefined | High | Confirmed gap | Phase 1 Track A: resolve from Stargile source. State machine not finalised until confirmed. |
| Movex sandbox environment not available | High | Unknown | Phase 2 hard gate: IT must confirm. Phase 3 Sprint 3 cannot begin without it. |
| ISO 13485 compliance gaps in new system | Critical | Low | Software Validation plan starts Phase 2. UAT is OQ evidence. Compliance is first-class, not afterthought. |
| IFS migration timing overlaps ECN build | High | Possible | ERP Adapter pattern by design. IFS stub in Phase 3 Sprint 4 validates interface completeness early. |
| Movex M3 API changes during development | Medium | Low | ERP Adapter isolates impact to adapter layer only. |
| Scope creep from 'Stargile used to...' | Medium | Likely | Retired Functionality List signed in Phase 1. All scope references the Behavioural Spec. |
| BOM concurrency — engineers overwrite each other | Medium | Possible | Optimistic locking with version columns and conflict resolution UI — see Section 7.3. |
| Movex date-based conflict errors (Status 50) | Medium | Certain | validate_payload pre-validation catches date conflicts before submission. |
| Parallel operation period extends too long | Medium | Possible | Max 4 weeks parallel. Active management of open Stargile ECNs from cutover announcement. |
| Single developer delivery risk | High | Possible | Contractor access confirmed available. Resource confirmed at Phase 2 gate. |
| Engineer resistance to new system | Low | Low | User pull factor confirmed. Track B involvement builds ownership. |

# 12. Resource Plan

| Resource | Phases | Purpose |
| --- | --- | --- |
| AI tooling (Claude API) | 1–4 | Source code analysis, documentation, development assistance |
| SME — Production Engineers | 1, 3 | Track B sessions, UAT participation |
| SME — Document Control / QA | 1, 3, 4 | Compliance requirements, UAT, Software Validation sign-off |
| SME — SMT Engineer | 1 | Dedicated SMT session — programme workflow confirmation |
| Backend developer (Python) | 2–4 | FastAPI, ERP Adapter, event bus, PostgreSQL |
| Frontend developer (React/TS) | 2–4 | React TypeScript UI, notifications, forms |
| IT — Windows Server infrastructure | 2–4 | Server provisioning, IIS, NSSM, ADCS certificate, Movex sandbox |
| Contractor (if needed) | 3 | Additional Phase 3 capacity — confirmed at Phase 2 gate |
| Movex test/sandbox environment | 3–4 | ERP integration testing — mandatory Phase 2 gate |
| PostgreSQL + App servers (on-premise) | 3–4 | Hardware for production and staging |
| ISO 13485 review time | 4 | Software Validation sign-off |
| Training delivery time | 4 | Sessions, materials, signed attendance records |

# 13. The ECN System as Organisational AI Platform Foundation

| ECN Decision | Platform Capability Enabled |
| --- | --- |
| Python/FastAPI backend | Every AI agent integrates natively. No translation layer required across any module. |
| ERP Adapter pattern | Platform survives Movex → IFS migration intact. All adapter-using systems are shielded simultaneously. |
| Event bus from day one | IoT projects and AI agents subscribe to ECN events without modifying the ECN system. |
| PostgreSQL audit log with hash chain | Structured, tamper-evident compliance data becomes AI training data. |
| OpenAPI specification | Agents discover and call ECN functions using standard tool-use patterns. |
| Behavioural Specification as Phase 1 gate | Every future system replacement (BOM, MSP, MES) starts with the same rigorous discovery — reusable process. |
| Retired Functionality List discipline | Formally decommissioning dead functionality — a discipline that carries to every future project. |
| ISO 13485 Software Validation framework | Reusable for every subsequent quality system tool in the programme. |
| On-premises Windows infrastructure design | Infrastructure patterns reusable for MES, BOM, MSP systems on the same stack. |
| BOM concurrency design (optimistic locking) | Pattern reusable for any shared-data editing across future platform modules. |

# Appendix A: Phase Timeline Summary

| Phase | Weeks | Gate Deliverables |
| --- | --- | --- |
| Phase 1 — Discovery | 1–3 | Behavioural Spec + ERP Adapter Interface + Retired Functionality List + Excel template decision + SMT session findings + Retention decision (QA signed) |
| Phase 2 — Architecture | 4–5 | ADR + Data Model + NFR baseline + Infra confirmed + Movex sandbox confirmed + Contractor confirmed + Build Plan |
| Phase 3 — Build | 6–17 | Working system + IFS adapter stub + Signed UAT report + Training materials + Parallel operation complete |
| Phase 4 — Cutover | 18–20 | Go-live + Software Validation (IQ/OQ/PQ) + Training records + Rollback procedure rehearsed + Stargile decommissioned |
| Total Programme | 20 weeks | Stargile replaced — Org AI Platform foundation established |

# Appendix B: Confirmed Happy Path (Branko Transcript, April 2018)

The following is the confirmed baseline ECN workflow from the April 2018 software validation session. This is the starting point for Phase 1 Track B — it must be validated as current before Phase 3 begins.

- Engineer creates a new ECN: title, customer reference, effective date. ECN number assigned — required for item upload template.

- Approval roles assigned: Document Control mandatory; SMT, Test, Validation conditional.

- Items uploaded via Excel template: mandatory fields (dark blue), engineering fields (light blue), purchasing fields (yellow, optional).

- BOM created: BOM number in row 2, component rows below with quantities and part numbers.

- Routes created or updated.

- ECN submitted for approval. Each approver reviews and approves with password confirmation.

- On full approval, ECN transitions to Status 50: Movex push attempted.

- If Movex push fails: engineer receives email. Error log viewable via right-click. Engineer corrects and retries via 'Update Movex' on worklist.

- On successful push: ECN transitions to Status 60.

- BOM revision number and change text updated manually in Movex PDS screen.

- Movex displays updated BOM with new revision as of effective date.

Known exception: date-based Movex conflicts. If effective date matches existing BOM line from-date, Movex returns error. The new system's validate_payload method must catch this before Status 50. ⚠ Gap: What happens after Status 60? The transcript does not show an explicit terminal state. Phase 1 Track A must resolve from Stargile source code.

# Appendix C: Architectural Decision Log

| Decision | Options Considered | Decision Made | Rationale |
| --- | --- | --- | --- |
| Backend language | Python/FastAPI, .NET (workspace standard), Node.js, Java | Python/FastAPI | Python is the primary language of every AI/ML and agent framework. All future AI agents integrate natively. The deviation from the .NET workspace standard is intentional and justified by the AI platform roadmap — documented here explicitly. |
| Database | PostgreSQL, SQL Server (Windows-native), MySQL | PostgreSQL | Open-source (no licence cost), strong ISO 13485 audit pattern support, JSONB for BOM flexibility, SQL directly queryable by AI agents. SQL Server ruled out on licence cost and weaker Python ecosystem tooling. |
| ERP coupling | Direct M3 calls, ERP Adapter pattern | ERP Adapter pattern | The Movex → IFS migration makes direct M3 coupling unacceptable. One interface, two implementations, zero ECN application rewrites at migration time. |
| Deployment model | Cloud (Azure/AWS), On-premises Windows Server | On-premises Windows Server | Organisational policy, data sensitivity, ISO 13485 auditability, internal network ERP connectivity. |
| Event bus | Redis Streams, RabbitMQ, PostgreSQL LISTEN/NOTIFY | Redis Streams (WSL2) with PostgreSQL fallback | Redis Streams recommended. If WSL2 unavailable, PostgreSQL LISTEN/NOTIFY is the fallback. Decision confirmed at Phase 2 gate after IT infrastructure review. |
| Notification system | Exchange SMTP + WebSocket, Teams webhooks, SaaS | Exchange SMTP + WebSocket | On-premises Windows infrastructure. No SaaS dependency. Exchange already deployed. Email delivery recordable for ISO 13485 audit. |
| Build vs commercial | Custom build, commercial ECN/PLM platform | Custom build | Domain well-bounded and fully visible. Team has developer access. Maximum integration flexibility and ERP adapter independence. |

# Appendix D: User Training Plan

## D.1 Training Materials (Phase 4 Deliverables)

| Material | Audience | Format |
| --- | --- | --- |
| System user guide (SOP) | All users | Written SOP with screenshots — stored in document management system |
| ECN creation walkthrough | Production Engineers | Step-by-step guide + screen recording |
| Approval workflow guide | Document Control, SMT, Test Engineers | Step-by-step guide + screen recording |
| Administrator guide | IT + designated admin | Technical reference document |
| Quick reference card | All users | 1-page laminated card for desk reference |

## D.2 Training Sessions

| Session | Audience | Timing | Duration |
| --- | --- | --- | --- |
| Production Engineer training | All Production Engineers | 2 weeks before go-live | 2 hours |
| Approver training | Document Control, SMT, Test Engineers | 2 weeks before go-live | 1 hour |
| Administrator training | IT + designated admin | 3 weeks before go-live | 2 hours |
| Train-the-trainer | 1 Production Engineer + 1 QA person | 3 weeks before go-live | 3 hours |

## D.3 Competency Assessment

Each user must demonstrate the following without assistance before go-live (assessed during UAT or a separate practical assessment):

- Production Engineer: create an ECN, upload items, create a BOM, submit for approval

- Approver: locate an ECN pending their approval, review, and approve or reject with a comment

- Administrator: create a user, assign a role, reset a password

Training records — signed attendance records with session date, trainer, attendee, topics, and attendee signature — are retained as quality records for the system operational life plus the ISO 13485-required retention period.

Document Version 2.0 — ECN Modernisation Programme — For Management Review