[PLATFORM NAME]

ENGINEERING INTELLIGENCE PLATFORM

Modernisation and Build Strategy  v2.0

| Version | 2.0 — For Management Review |
| --- | --- |
| Programme | Engineering / IT Modernisation — SRX Manufacturing |
| Replaces | Stargile (Java ECN) + PLMServer (PHP BOM / Supplier) |
| Iteration 1 modules | ECN · BOM · Supplier Intelligence |
| Future modules | Routes · MSP · MES |
| Sites | Melbourne Site (Movex permanent) · J B Site (Movex → IFS) |
| Platform name | To be decided — see Section 1 |

| Version | Key changes from previous version |
| --- | --- |
| v1.0 | Initial strategy: unified platform, three modules, four-phase programme, tech stack, adapter patterns |
| v2.0 | Corrected data authority model (Movex remains SOT for committed BOMs); corrected Stargile MI interface (own Java classes, not movex-rest-api); two-site deployment architecture; Mermaid diagrams added throughout |

# Section 1 — Platform Naming Decision

For management review and decision. Replace [PLATFORM] throughout with the chosen name. The recommendation is DELTA — the universal symbol for change. See reasoning below.

| Name | Meaning and Reasoning | Recommendation |
| --- | --- | --- |
| DELTA | The universal symbol for change — Δ. Every ECN is literally a delta to a BOM. Works identically in all European languages. The only candidate that directly describes what the platform does rather than offering a metaphor. | ⭐ Recommended |
| NEXUS | The connection point — ECN, BOM, supplier intelligence, routes, both ERPs. Latin root, cross-language. | Strong |
| HELIX | Upward spiral / DNA structure. BOM is the genetic code; ECN is the revision mechanism. Internationally neutral. | Strong |
| MERIDIAN | The reference line. Platform is the engineering change authority; Movex is the production record. Professional gravitas. | Strong |
| VERTEX | Meeting point of multiple lines. ECN, BOM, supplier intelligence, MES all converge. Mathematical, clean. | Solid |
| VEGA | Brightest star in the northern sky. Short, modern, internationally recognised, Nordic resonance. | Solid |
| LUMEN | Light and clarity. Latin root works cross-language. | Solid |
| FORGE | Strong manufacturing metaphor. Anglo-industrial connotation may feel less natural in Scandinavian group context. | Lower preference |
| KLAR | Swedish/Norwegian for clear/ready. Clean but may be opaque in English documentation. | Lower preference |

# Executive Summary

SRX Manufacturing operates two independent legacy systems — Stargile (Java ECN) and PLMServer (PHP BOM and Supplier Intelligence) — to manage what is fundamentally a single, interconnected workflow. The [PLATFORM] Engineering Intelligence Platform replaces both systems with a unified, AI-ready platform.

Three key facts confirmed in v2.0 that were either incorrect or absent in v1.0:

| Confirmed fact | Architectural implication |
| --- | --- |
| Stargile has its own Java MI interface calling Movex MI API directly — it does not use movex-rest-api | Phase 1 Track A must produce an MI program inventory and gap analysis. movex-rest-api must be extended before Sprint 3. This is a new Phase 1 gate deliverable. |
| Movex remains the source of truth for committed production BOMs — the platform manages change workflow and draft state | The 'platform owns the BOM' framing in v1.0 was imprecise and risks bidirectional sync problems. Corrected in Section 3. |
| Two sites under same SRX entity — Site A Movex permanent, Site B Movex now then IFS, later splitting across two countries | Site-aware configuration, not multi-tenancy. Same codebase, different environment files per site. Country split is a deployment configuration change — no architectural changes required. |

### Iteration 1 — Three Modules, Built Together

| Module | Replaces | Core improvement |
| --- | --- | --- |
| ECN Module | Stargile (Java) | Modern approval workflow · ISO 13485 audit trail · ERP Adapter for IFS · MAS v2.0 agent · validate_payload pre-check |
| BOM Module | PLMServer BOM management | Version history · BOM comparison tool · Optimistic locking · Shared draft with ECN · No re-upload |
| Supplier Intelligence | PLMServer APIManager | 13 min → under 90 sec · Parallel async · Redis cache · 6 suppliers · Circuit breakers · Real-time progress |

# 2. Current Situation — Two Systems, One Problem

Diagram note: Full interactive Mermaid diagrams are included in the accompanying Markdown file (Engineering_Intelligence_Platform_Strategy_v2.md). These render in GitHub, VS Code, Notion, or any Mermaid-compatible viewer. The visual representations below communicate the same architectural content.

## 2.1 Current Architecture

Diagram 1 — Current state: two independent legacy systems

| Layer | Stargile (ECN) | PLMServer (BOM/Supplier) |
| --- | --- | --- |
| Language / stack | Java — direct MI API calls to Movex | PHP 7.4 / MySQL / Apache |
| ERP integration | Own Java classes → Movex MI API directly | SQL Server view (read-only from Movex) |
| Users | Production Engineers, Document Control, SMT, Test Engineers | Engineers/Planners (2/8 active), CBMs, Purchasing |
| Key problem | Status 50 failures routine · no IFS path · own MI interface not shared | 13+ min BOM processing · NPS -40 · SSL disabled |
| Shared layer | Movex is the only shared data layer between both systems |  |
| Missing | No integration between Stargile and PLMServer — engineers manually re-upload BOM data |  |

## 2.2 What Stargile's ERP Interface Actually Is

Stargile connects to Movex through its own Java classes calling the Movex MI API directly. This is not movex-rest-api. Phase 1 Track A must extract the complete MI program inventory from Stargile's Java source — program names, transaction types, input and output fields, known quirks — and produce a gap analysis against movex-rest-api's current coverage. The gap becomes a specification of new endpoints the .NET team must add before Sprint 3.

| Phase 1 Track A — Stargile MI analysis | Required output |
| --- | --- |
| Step 1: Extract MI call inventory from Java source | List of every MI program called by Stargile — program name, transaction, input fields, output fields |
| Step 2: Cross-reference against movex-rest-api endpoints | Gap list: MI operations Stargile uses that movex-rest-api does not expose |
| Step 3: Specify new movex-rest-api endpoints | Specification handed to .NET team in Phase 2 |
| Step 4: .NET team adds endpoints | Must be deployed to staging before Sprint 3 ERP integration begins |

## 2.3 The Engineer Workflow Today

| Step | System | Pain point |
| --- | --- | --- |
| Create ECN, assign approvers | Stargile | Manual Excel upload. Status 50 failures routine — date conflicts require workaround. |
| Approval routing | Stargile | Manual — no automated reminders or escalation. |
| Commit BOM change to Movex | Stargile (Java MI → Movex) | Manual BOM revision update in Movex PDS screen after Status 60. |
| Re-upload BOM to PLMServer | PLMServer | Manual re-entry or file upload — no automatic sync from Movex. |
| Run supplier pricing | PLMServer | 13+ minutes for 100-part BOM. No progress feedback. Users think system is frozen. |
| Review, export for Purchasing | PLMServer | Manual Excel export. No BOM comparison. NPS -40. |

# 3. Data Authority Model — The Correct Architecture

Diagram 2 — Layered authority: platform manages change workflow; Movex holds committed BOM

## 3.1 The Key Distinction

The v1.0 strategy described the platform as 'owning the BOM.' This was imprecise and required correction. In a manufacturing operation under ISO 13485, Movex drives MRP, production orders, purchasing, and inventory. Other departments may update BOMs in Movex outside the ECN process. If the platform claimed to own the BOM, it would immediately face a bidirectional synchronisation problem: Movex changes something, the platform does not know, and the platform's copy becomes stale.

## 3.2 Layered Authority — What Each System Owns

| Data | Authority | Lives in | Why |
| --- | --- | --- | --- |
| Committed production BOM — what is in production | Movex | Movex | MRP, production orders, purchasing all depend on Movex being authoritative. ISO 13485 auditors expect it. |
| Proposed BOM change — the ECN draft | Platform | Platform database | Change workflow is the platform's core function. |
| ECN history — every change ever raised | Platform | Platform database | ISO 13485 audit trail. Immutable. Agents query this. |
| BOM version chain — history of revisions | Platform | Platform database | Rich history of every ECN commit. Not available in Movex. |
| Supplier intelligence — pricing, availability | Platform | Platform DB + Redis cache | Movex has no supplier API integration. |
| Compliance flags — RoHS/REACH/WEEE | Platform | Platform database | From Octopart API and manual Document Control entry. |

## 3.3 How the Platform and Movex Interact

| Action | Direction | Mechanism |
| --- | --- | --- |
| ECN approved — BOM change committed | Platform → Movex | ERP Adapter push_bom() via movex-rest-api |
| New BOM loaded for ECN proposal | Movex → Platform | Engineer uploads or ERP Adapter reads current committed BOM |
| AI agent queries change history | Agent → Platform | GET /boms/{id}/history — from platform database |
| AI agent needs current production BOM | Agent → Platform → ERP Adapter → Movex | Platform queries via adapter — not platform database |

## 3.4 Why This Model Is Correct

- No synchronisation risk — Movex can be updated by other processes without breaking platform integrity

- ISO 13485 aligned — auditors expect Movex to be authoritative for the production BOM; the platform provides the change traceability layer on top

- Multi-site safe — both Site A and Site B keep Movex as their production authority; the ERP Adapter controls where each site commits

- AI value unchanged — change history, approvals, supplier intelligence, and BOM version chain all live in the platform

- IFS migration safe — Site B's production authority changes to IFS; the model is unchanged; the platform still pushes through the adapter

# 4. Two-Site Deployment Architecture

Diagram note: Full interactive Mermaid diagrams are included in the accompanying Markdown file (Engineering_Intelligence_Platform_Strategy_v2.md). These render in GitHub, VS Code, Notion, or any Mermaid-compatible viewer. The visual representations below communicate the same architectural content.

## 4.1 Configuration, Not Architecture

Both sites are the same SRX entity. The platform does not need multi-tenancy — separate databases and authentication domains. It needs site-aware ERP adapter configuration: the same codebase, different environment files per site. When Site B splits across two countries, that is a deployment configuration change requiring no platform code changes.

Diagram 3 — Two-site deployment: same Docker images, site-specific environment files

|  | Site A | Site B (current) | Site B (future) |
| --- | --- | --- | --- |
| ERP | Movex — permanent | Movex | IFS |
| ERP Adapter | MovexRestAdapter | MovexRestAdapter | IFSAdapter (swap in env config) |
| Platform codebase | Identical | Identical | Identical |
| Environment file | ERP_ADAPTER=movex SITE_ID=site_a | ERP_ADAPTER=movex SITE_ID=site_b | ERP_ADAPTER=ifs SITE_ID=site_b |
| Country split | Not applicable | Single country | Two instances — one per country, same config pattern |
| Code changes at IFS migration | None | None — env file change only | None |

## 4.2 Deployment Option (Recommended)

Two instances, shared codebase: each site runs its own Docker Compose stack — its own PostgreSQL, its own Redis, its own environment file — deployed from the same Git repository and the same Docker images. Data is separated at the instance level. Each site has an independent ISO 13485 Software Validation record. When Site B splits across two countries, the Site B instance is cloned into two new instances.

## 4.3 Site B IFS Migration Sequence

Diagram 4 — Site B IFS migration: same platform call, different adapter target

| Step | Before migration (Movex) | After migration (IFS) |
| --- | --- | --- |
| Engineer submits ECN | ECN workflow in [PLATFORM] | ECN workflow in [PLATFORM] — unchanged |
| Approval routing | [PLATFORM] approval engine | [PLATFORM] approval engine — unchanged |
| Platform calls ERP Adapter | push_bom(payload) — same interface | push_bom(payload) — same interface |
| Adapter target | MovexRestAdapter → HTTP → movex-rest-api → Movex | IFSAdapter → IFS API |
| Movex / IFS result | Movex confirms update | IFS confirms update |
| Platform code change | None | None — only site_b.env ERP_ADAPTER value changes |

# 5. Platform Architecture

Diagram note: Full interactive Mermaid diagrams are included in the accompanying Markdown file (Engineering_Intelligence_Platform_Strategy_v2.md). These render in GitHub, VS Code, Notion, or any Mermaid-compatible viewer. The visual representations below communicate the same architectural content.

## 5.1 Architecture Overview

Diagram 5 — Platform architecture: three modules on one foundation, two adapter patterns

Three modules on one foundation, sharing one PostgreSQL database, one Redis instance, one authentication layer, one audit log, and one event bus. No integration contracts between modules. One ERP Adapter, one Supplier Adapter. Platform name [PLATFORM] replaces both legacy systems.

| Layer | Component | Technology |
| --- | --- | --- |
| Frontend | SM-Portal module (or standalone — Phase 1 decision) | React 18 + TypeScript |
| ECN Module | Change notes · approval routing · ISO 13485 audit trail · ERP push | Python/FastAPI |
| BOM Module | Draft BOM · version history · comparison · optimistic locking · RoHS flags | Python/FastAPI |
| Supplier Intelligence | 6 supplier adapters · parallel async · Redis cache · circuit breakers | Python/FastAPI + Celery |
| Shared database | Single PostgreSQL shared across all modules — BOM, ECN, Parts, Offers, Audit | PostgreSQL 16 |
| Shared event bus + cache | Redis Streams (event bus) + Redis key-value (supplier cache) — same instance | Redis 7 |
| Authentication | JWT + RBAC + AD integration — single auth across all modules | FastAPI security + AD |
| ERP Adapter | Abstract interface → MovexRestAdapter → movex-rest-api (.NET) → Movex / IFS | Python HTTP client |
| Supplier Adapter | Abstract interface → 6 SupplierAdapter implementations | Python async (aiohttp) |
| Celery worker | Background supplier API fan-out · OAuth token proactive refresh | Celery + Redis broker |
| MAS v2.0 agents | expert-[platform]-ecn · expert-[platform]-bom registered in agent registry | Sprint 5 deliverable |

## 5.2 The ERP Adapter — Corrected for Stargile's MI Interface

Diagram 6 — ERP Adapter: platform calls movex-rest-api; Stargile had own Java MI interface (reference only)

| Path | Stack | Status |
| --- | --- | --- |
| Platform ECN/BOM → ERPAdapter interface → MovexRestAdapter → HTTP → movex-rest-api (.NET) → MI API → Movex | Python → .NET REST → MI | Sprint 3 — production |
| Platform ECN/BOM → ERPAdapter interface → IFSAdapter → IFS API | Python → IFS API | Sprint 4 stub, feature-flagged — Site B future |
| Stargile → own Java MI classes → MI API → Movex (reference — legacy path being replaced) | Java → MI | Current — to be decommissioned |

The movex-rest-api must be extended in Phase 2 to cover MI operations that Stargile uses but movex-rest-api does not currently expose. This extension is a hard Sprint 3 dependency. If extensions are not ready when Sprint 3 begins, ERP integration work is deferred within Sprint 3 until they are.

## 5.3 Async Parallel Supplier Processing

Diagram 7 — Sequential today vs parallel async in platform

| Approach | Processing model | Time for 100 parts / 6 suppliers |
| --- | --- | --- |
| PLMServer today | Sequential: one part, one supplier, wait, next — no cache, no retry, SSL disabled | ~1,200 seconds (20 minutes) |
| Platform — parallel async | asyncio.gather: all parts × all suppliers concurrently, per-supplier semaphore (rate limit) | Under 90 seconds |
| Platform — cache hit | Redis key-value lookup: cached result returned immediately, no API call | < 1 second |
| Platform — degraded (1 supplier down) | Per-supplier circuit breaker: remaining 5 suppliers continue, stale cache returned for down supplier | Under 90 seconds |

# 6. Four-Phase Programme — 24 Weeks

Diagram 8 — 24-week programme timeline (Gantt diagram in Mermaid file)

| Phase | Weeks | Focus | Gate Deliverable |
| --- | --- | --- | --- |
| Phase 1 — Discovery | 1–4 | Two-system analysis · adapter interfaces · Stargile MI gap analysis | ECN Spec + BOM/Supplier Spec + All adapter interfaces + MI gap analysis + SM-Portal decision + Retention decisions + Two-site model + Vault entries |
| Phase 2 — Architecture | 5–6 | Shared data model · build plan · movex-rest-api extensions | ADR + Data model + NFRs + Docker confirmed + Movex sandbox + Supplier test credentials + movex-rest-api extensions scheduled |
| Phase 3 — Build | 7–20 | Five sprints across three modules | Working platform + IFS stub + Site B config + Both MAS agents + Sprint 3 perf demo + UAT both modules + Training materials |
| Phase 4 — Cutover | 21–24 | Go-live both sites and systems · validation · handover | Go-live + IQ/OQ/PQ + Training records + Rollback rehearsed + Both systems decommissioned + Vault handover |

PHASE 1 — Discovery Weeks 1–4 — three parallel tracks + MI gap analysis

Start Phase 1 by running /m3-lookup in the Knowledge Vault before opening any source file. PLMServer's analysis assets (PLMServer_Complete_Analysis.md + plm-tables.sql) are the primary PLMServer Track A inputs — do not re-derive documented analysis. Stargile's Java MI interface must be extracted from source; SME sessions and MI documentation cover the gap if source is delayed.

### Track A — Source Code and MI Gap Analysis

- PLMServer: validate January 2025 analysis against live system. Confirm six supplier integrations, OAuth lifecycle, price break algorithms. Confirm which features are genuinely used (20% adoption).

- Stargile: extract complete MI program inventory from Java source — program name, transaction type, all input/output fields, known quirks. Cross-reference against movex-rest-api. Produce gap specification for .NET team.

- Add PLMServer + Stargile project entries to vault/projects/. Add ECN (ISO 13485) + BOM (RoHS/REACH) compliance notes to vault/compliance/.

### Track B — SME Behavioural Sessions

- Stargile sessions: full ECN state machine (resolve Status 60 exit), all exception paths, Excel template decision, SMT programme workflow, unused functionality sign-off

- PLMServer sessions: which workflows are genuinely used, supplier list and regional needs, RoHS/REACH/WEEE requirements, BOM approval and export workflow

- Shared sessions: data retention decisions (both systems), SM-Portal architecture review, two-site deployment confirmation with IT

### Track C — Adapter Interface Definitions

- ERP Adapter: push_item, push_bom, push_route, get_errors, retry_push, validate_payload — calls movex-rest-api over HTTP

- Supplier Adapter: search_part, get_pricing, get_alternatives, check_compliance, get_availability — one implementation per supplier

- BOM Comparison Service: compare(bom_a_id, bom_b_id) → DiffResult — added, removed, changed lines with field-level diff

| Phase 1 Gate Deliverables — all must be complete before Phase 2 |  |  |
| --- | --- | --- |
| Deliverable | Owner | Sign-off |
| ECN Behavioural Specification (full state machine, all roles, exception paths) | Developer + SMEs | Production Engineer, Document Control |
| BOM/Supplier Behavioural Specification | Developer + SMEs | Engineer, CBM, Purchasing |
| ERP Adapter Interface | Developer | IT / Architecture |
| Supplier Adapter Interface (all six suppliers) | Developer | IT / Architecture |
| BOM Comparison Service Interface | Developer | IT / Architecture |
| Stargile MI gap analysis + movex-rest-api extension specification | Developer + .NET team | IT / .NET team lead |
| Retired Functionality Lists (one per legacy system) | Developer + SMEs | Manager + SMEs |
| Excel template decision (ECN) | SMEs | Production Engineer |
| SM-Portal integration decision | Developer + IT | IT, Manager |
| Data retention decisions — ECN (ISO 13485) + BOM (pricing/compliance history) | Developer + QA | QA sign-off |
| Two-site deployment model confirmed | Developer + IT | IT, Manager |
| Vault entries — both projects + compliance notes + all ADRs | Developer | Vault commit |

PHASE 2 — Architecture Decision and Build Plan Weeks 5–6

| Phase 2 Gate Conditions — ALL must be met before Phase 3 begins |  |  |
| --- | --- | --- |
| Gate Condition | Owner | If Not Met |
| Architecture Decision Record complete | Developer | Extend Phase 2 |
| Shared data model finalised | Developer | Extend Phase 2 |
| NFRs baselined | Developer + IT | Extend Phase 2 |
| movex-rest-api gap endpoints specified and work scheduled | Developer + .NET team | Sprint 3 ERP integration deferred until ready |
| Movex test/sandbox environment confirmed | IT | Phase 3 cannot begin |
| Docker on Windows Server confirmed working | IT | Phase 3 cannot begin |
| Supplier API test credentials confirmed (all 6) | IT | Sprint 3 supplier work cannot begin |
| Two-site deployment model agreed | IT + Manager | Sprint 1 environment setup cannot be finalised |
| All data retention decisions signed by QA | QA | Phase 3 cannot begin |

PHASE 3 — Build — Five Sprints Across Three Modules Weeks 7–20

Diagram 9 — Sprint sequence (flowchart in Mermaid file)

| Sprint | Weeks | Key Deliverables |
| --- | --- | --- |
| Sprint 1 | 7–9 | Platform scaffolding at c:/Projects/[Platform]/; Docker on Windows Server; commit hook installed (vault connected from Sprint 1); AD authentication; role model for all user types; SM-Portal module or standalone per Phase 1 decision; ECN creation UI; BOM creation UI; Site A and Site B environment files |
| Sprint 2 | 10–12 | ECN approval routing engine; BOM version history; BOM management with optimistic locking and conflict resolution UI; BOM comparison tool (top PLMServer gap — built Sprint 2, not deferred); item upload (Excel or native form per SME decision) |
| Sprint 3 | 13–15 | All 6 SupplierAdapter implementations — parallel async, Redis cache, circuit breakers, rate limit semaphores; DigiKey OAuth proactive refresh; exponential backoff retry; real-time WebSocket progress; ERP Adapter MovexRestAdapter implementation vs Movex sandbox; validate_payload pre-check |
| Sprint 4 | 16–18 | Exchange SMTP + WebSocket notifications; Status 50 error recovery; RoHS/REACH/WEEE compliance flags on Part entity; Octopart alternative component search; IFS adapter stub (feature-flagged off); Site B env config pointing to IFS stub for validation |
| Sprint 5 | 19–20 | Immutable audit log with SHA-256 hash chain; ISO 13485 compliance reporting; BOM pricing and cost reports for Purchasing; expert-[platform]-ecn + expert-[platform]-bom agent registrations; Sprint 3 performance demo to engineers; end-to-end UAT both modules; training materials |

Sprint 3 mandatory milestone — performance demonstration to engineers: Show 100-part BOM processing with real engineer data BEFORE Sprint 5 UAT. PLMServer's NPS is -40 because engineers were burned by 13-minute processing. Demonstrate sub-90-second performance before asking for trust. This is a Sprint 3 definition of done item.

PHASE 4 — Cutover, Validation and Handover Weeks 21–24 — two independent cutover sequences

Diagram 10 — Cutover sequence (sequence diagram in Mermaid file)

| Step | Stargile (ECN) | PLMServer (BOM/Supplier) |
| --- | --- | --- |
| Pre-condition | All open ECNs at terminal state — hard ISO 13485 rule. No cutover with open ECNs. | All active BOM workflows complete or recreatable. |
| Training | All users trained, attendance recorded (ISO 13485 quality record) | All users trained before go-live |
| Go-live | New ECNs in [PLATFORM] only. Stargile set to read-only. | New BOM evaluations in [PLATFORM] only. PLMServer set to read-only. |
| Hypercare window | 72 hours — compliance-critical | 48 hours |
| Rollback window | 30 days — then historical data migration and decommission | 30 days — then archive PLMServer database |
| Historical data | Migrate Stargile ECN records to platform with archived = true flag (QA signed) | Archive PLMServer database — read-only access for 12 months |

### Software Validation Documentation (ISO 13485 — ECN Module)

| Document | Evidence Source |
| --- | --- |
| Installation Qualification (IQ) | Deployment runbook execution log + Docker image digest confirming exact version deployed |
| Operational Qualification (OQ) | ECN Behavioural Specification (Phase 1) + ECN UAT Report (Phase 3) — designed in Phase 1 to serve double duty |
| Performance Qualification (PQ) | Pilot period monitoring data from production |

# 7. ECN State Machine

Diagram 11 — ECN state machine (stateDiagram-v2 in Mermaid file)

| State | Status Code | Description | Exit Condition |
| --- | --- | --- | --- |
| Draft | 10 | Created by engineer — not yet submitted | Engineer submits ECN |
| Submitted | 20 | Routed to required approvers | First approver acts |
| Under Review | 30 | Approvals in progress — each approver acts with password confirmation | All required approvals received |
| Approved | 40 | All approvals received — validate_payload check initiated | ERP push initiated (after pre-check passes) |
| ERP Pending | 50 | push_bom() submitted to movex-rest-api — awaiting confirmation | Push result received |
| ERP Failed | 55 | movex-rest-api returned an error response | Engineer enters error recovery |
| Error Recovery | 57 | Engineer correcting payload — date conflict, field error, etc. | Retry submitted |
| ERP Success | 60 | Movex confirmed the BOM update via movex-rest-api | Post-push notifications sent |
| Completed | 70 | Explicit terminal state — immutable ISO 13485 audit endpoint | None — record immutable forever |
| Rejected | 90 | Approver rejected the ECN — terminal | None — record immutable forever |

Status 70 (Completed) is a new explicit terminal state. The April 2018 transcript showed Status 60 as the apparent endpoint but did not confirm a further terminal state. Phase 1 Track A must resolve from Stargile's Java source. If Stargile's Status 60 is already a true terminal state, the state machine collapses Status 60 and 70 into one with the immutability semantics of Status 70.

The validate_payload method is called before the ERP push is initiated — before the ECN reaches Status 50. It pre-checks effective date conflicts (the known cause of date-conflict Status 50 failures documented in the April 2018 transcript) and payload validity against movex-rest-api's input requirements. Engineers receive a clear, actionable error before any MI transaction is attempted — eliminating this class of Status 50 failure entirely.

# 8. Non-Functional Requirements

## 8.1 Performance

| Requirement | Target | Rationale |
| --- | --- | --- |
| Page load time | < 3 seconds on local network | Engineering workstation standard |
| API response (standard operations) | < 500ms at 95th percentile | Workflow productivity |
| API response (ERP push via movex-rest-api) | < 30 seconds | Dependent on movex-rest-api + Movex SLA |
| BOM processing — 100 parts / 6 suppliers | < 90 seconds | vs 13+ minutes today — PLMServer analysis |
| BOM processing — 50 parts / 6 suppliers | < 45 seconds | Typical customer order BOM |
| Supplier cache hit rate (repeat MPNs) | > 70% | Redis 4-hour TTL on pricing data |
| BOM comparison (500-line BOM) | < 3 seconds | Diff algorithm performance target |
| Audit log query (12 months) | < 10 seconds | ISO 13485 compliance review speed |
| Concurrent users | 20 simultaneous without degradation | 7–8 engineers + CBMs + Purchasing |

## 8.2 Supplier Integration Resilience

| Behaviour | Implementation |
| --- | --- |
| Per-supplier circuit breaker | Each SupplierAdapter has independent health state. DigiKey down → Mouser/Element14/etc. continue. |
| Stale cache fallback | If supplier unavailable and cached result exists (even expired), return with staleness warning — not an error. |
| Partial results | Return available results immediately. Notify via WebSocket when additional results arrive. |
| Rate limit management | Per-supplier semaphore. DigiKey: 1,000/day. Element14: 100/min. Mouser: 1,000/hour. Excess requests queued, not dropped. |
| OAuth token proactive refresh | DigiKey tokens refreshed 5 minutes before expiry by Celery worker. Eliminates PLMServer crash-on-expiry. |

## 8.3 Scalability

| Requirement | Target |
| --- | --- |
| User growth | 100 users without architectural change — accommodates group rollout across sites |
| BOM records | 50,000 BOMs with full version history |
| MPN catalogue | 500,000 parts without query degradation |
| Site instances | Designed for 2; extendable by configuration — no architectural changes |

# 9. Infrastructure and Hosting

On-premise, Windows Server. Docker on Windows Server via WSL2. Two site instances — same Docker images, different environment files. Consistent with movex-rest-api, SM-Portal, and MyInvois-Service.

Diagram 12 — Two-site Docker deployment (flowchart in Mermaid file)

## 9.1 Docker Compose Services (per site instance)

| Service | Image | Purpose |
| --- | --- | --- |
| platform-app | Python/FastAPI (custom) | All three Iteration 1 modules via FastAPI routers |
| platform-db | PostgreSQL 16 | Shared data model — BOM, ECN, Parts, Supplier Offers, Audit Log |
| platform-redis | Redis 7 | Event bus (Redis Streams) + Supplier cache (key-value with 4-hr TTL) |
| platform-worker | Python Celery + Redis | Background supplier API fan-out · OAuth token refresh · long-running tasks |

## 9.2 Server Spec (per site)

| Server | Role | Minimum Spec |
| --- | --- | --- |
| App Server | Docker host — app, redis, worker; IIS reverse proxy on host | Windows Server 2019+, 16 cores, 32 GB RAM, 200 GB SSD |
| DB Server | PostgreSQL 16 — container or native per IT convention | Windows Server 2019+, 8 cores, 32 GB RAM, 1 TB SSD |
| Staging Server | Mirror of production — logically separated per site | Same spec as production — separated before go-live |

## 9.3 Network Topology

[Engineers / CBMs / Purchasing]

│  HTTPS port 443  (ADCS internal CA certificate)

▼

[IIS on App Server — host machine]

│  HTTP → localhost:8000

▼

[platform-app — FastAPI]

│

├── [platform-db — PostgreSQL]    Docker internal network

├── [platform-redis — Redis]      Docker internal network

├── [platform-worker — Celery]    Docker internal network

├── [movex-rest-api — .NET]       Internal network (existing)

└── [External Supplier APIs]      HTTPS outbound — TLS ENABLED

All outbound supplier API calls use HTTPS with TLS verification enabled (verify=True). This directly corrects PLMServer's 'verify': false security risk that exposed supplier credentials to potential man-in-the-middle attacks.

# 10. Security Design

## 10.1 PLMServer Security Issues — All Corrected

| PLMServer issue | Severity | Resolution in [PLATFORM] |
| --- | --- | --- |
| HTTPS disabled — all traffic over HTTP | Critical | IIS enforces HTTPS. ADCS certificate. HTTP → HTTPS redirect. |
| SSL verification disabled ('verify': false) | Critical | All Python HTTP clients: verify=True. TLS on all supplier API calls. |
| Raw SQL queries — SQL injection risk | High | SQLAlchemy ORM parameterised statements. Raw string queries prohibited. |
| OAuth tokens not refreshed proactively | High | Celery worker refreshes DigiKey tokens 5 min before expiry. |
| No rate limiting on API calls | Medium | Per-supplier semaphore with configurable per-supplier limits. |
| No input validation | High | Pydantic models validate all inputs server-side before business logic. |

## 10.2 Authentication

JWT tokens in HTTP-only cookies (not localStorage — prevents XSS token theft). Access tokens: 15 minutes. Refresh tokens: 8 hours (one shift) with server-side revocation list in Redis. Active Directory integration recommended — engineers use Windows credentials; leavers automatically locked out when AD account is disabled.

Approval actions require password re-confirmation at the moment of approval — ISO 13485 non-repudiation requirement.

## 10.3 RBAC Matrix

| Permission | Prod Eng | Doc Control | CBM | Purchasing | SMT/Test | Admin |
| --- | --- | --- | --- | --- | --- | --- |
| Create / edit ECN | ✓ | — | — | — | — | — |
| Approve ECN | — | ✓ | — | — | ✓ | — |
| Create / edit BOM | ✓ | — | — | — | — | — |
| Upload BOM | ✓ | — | ✓ | — | — | — |
| Run supplier pricing | ✓ | — | ✓ | ✓ | — | — |
| Approve BOM for Purchasing | — | — | ✓ | — | — | — |
| Export BOM for ordering | — | — | — | ✓ | — | — |
| View compliance reports | — | ✓ | — | ✓ | — | ✓ |
| View audit log | — | ✓ | — | — | — | ✓ |
| Manage users / roles | — | — | — | — | — | ✓ |
| Configure supplier APIs | — | — | — | — | — | ✓ |

## 10.4 Audit Trail Security

-- Application user has INSERT + SELECT on audit_log only

REVOKE UPDATE, DELETE ON audit_log FROM platform_app_user;

Immutability enforced at database permission level — not only in application code. SHA-256 hash chain across all rows detects any post-write modification. Validation query runs nightly as part of backup verification.

# 11. MAS v2.0 and Knowledge Vault Integration

## 11.1 Two Agent Registrations — Sprint 5 Deliverables

| Agent | Capability | Endpoint |
| --- | --- | --- |
| expert-[platform]-ecn | Query ECN status by ID or customer ref | GET /ecns/{id} |
| expert-[platform]-ecn | Query approval state | GET /ecns/{id}/approvals |
| expert-[platform]-ecn | Subscribe to ECN events | Redis Streams ecn.* |
| expert-[platform]-ecn | Pre-validate a BOM change | POST /validate/bom |
| expert-[platform]-bom | Query BOM version history | GET /boms/{id}/history |
| expert-[platform]-bom | Compare two BOM revisions | GET /boms/compare?a={id}&b={id} |
| expert-[platform]-bom | Query supplier availability for a part | GET /parts/{mpn}/availability |
| expert-[platform]-bom | Query compliance flags for a part | GET /parts/{mpn}/compliance |
| expert-[platform]-bom | Subscribe to BOM events | Redis Streams bom.* |

## 11.2 Knowledge Vault Integration Points

| Phase | Action | Vault Skill |
| --- | --- | --- |
| Phase 1 — before Track A | Run /m3-lookup for all known Stargile MI programs and PLMServer M3 calls | /m3-lookup |
| Phase 1 — Track A | Add PLMServer + Stargile project entries; ECN + BOM compliance notes; Stargile MI gap ADR | Manual + /adr |
| Phase 2 | Record full Architecture Decision Record entries | /adr |
| Phase 3 — Sprint 1 | Install commit hook at c:/Projects/[Platform]/ — vault connected from day 1 | install-hooks.sh |
| Phase 3 — Sprint 5 | Register both agents in c:/Projects/.github/agents/manifest.json | Manual |
| Phase 4 | /mine both cutover transcripts; /runbook both rollback procedures; /review month 1 | /mine /runbook /review |

# 12. Compliance

| Regime | Scope | Module | Key Requirements |
| --- | --- | --- | --- |
| ISO 13485 | Medical device manufacturing quality | ECN | Immutable audit trail; non-repudiable approvals; IQ/OQ/PQ Software Validation; record retention for device lifetime + jurisdiction period |
| RoHS / REACH / WEEE | EU and APAC environmental compliance | BOM + Supplier | Compliance flags per component; validated at BOM edit; flag raised when non-compliant part added; reportable per BOM line |
| ISO 9001 | General quality management | Platform-wide | Audit trail; document control; corrective action process |

# 13. Risk Register

| Risk | Impact | Likelihood | Mitigation |
| --- | --- | --- | --- |
| Stargile MI gap analysis reveals large movex-rest-api extension scope | High | Possible | Phase 1 Track A produces the spec. .NET team scopes in Phase 2. If large, Sprint 3 ERP work sequenced after extensions deployed to staging. |
| Stargile source code not obtained before Phase 2 | High | Possible | SME sessions + MI API documentation cover the spec. Phase 2 proceeds with documented gaps. |
| PLMServer engineer adoption low despite improvements | Medium | Medium | Sprint 3 performance demo before UAT. Show 90-second processing with real engineer data. |
| Supplier API test credentials not confirmed before Sprint 3 | High | Possible | Phase 2 hard gate — all six required. Sprint 3 cannot begin without them. |
| Site B IFS migration timing overlaps platform build | High | Possible | IFS adapter stub Sprint 4 validates interface. Migration can begin from confirmed contract. |
| Two-site configuration drift | Medium | Low | Environment files in Git (secrets excluded). Deployment runbooks per site in vault. |
| SM-Portal integration introduces Sprint 1 scope risk | Medium | Possible | Phase 1 Track C surfaces early. Standalone fallback documented. Sprint 1 not blocked. |
| movex-rest-api extensions not ready for Sprint 3 | High | Possible | Phase 2 gate: extensions scheduled and estimated. Sprint 3 ERP work deferred if needed. |
| ISO 13485 audit during build | Critical | Low | Software Validation plan starts Phase 2. Behavioural Spec + UAT designed as dual-purpose evidence. |

# 14. Business Case Summary

| Benefit | Annual Value | Source |
| --- | --- | --- |
| BOM processing time savings (13 min → 90 sec) | ~$225,000/year | PLMServer analysis: ~3,000 engineer-hours/year @ $75 |
| Better supplier pricing — automated best-price | ~$100,000/year | PLMServer analysis: 2% on $5M parts spend |
| Reduced BOM rework errors | ~$24,000/year | PLMServer analysis |
| Engineer retention — frustration reduced | ~$30,000/year | PLMServer analysis: 2 fewer replacements |
| ECN efficiency — approval automation | Unquantified | Stargile friction eliminated |
| IFS migration risk reduction | Unquantified — strategic insurance | ERP Adapter pattern; single interface for both sites |
| Two-site from one codebase | Unquantified — operational saving | Configuration, not additional development |
| Total quantified annual benefit | ~$379,000/year | PLMServer analysis baseline |

The PLMServer analysis calculated a 7.3-month payback period and 65% ROI in year 1 for the BOM module alone. [PLATFORM] delivers all of that benefit plus the ECN replacement, both-site IFS migration path, and the Organisational AI Platform foundation.

# 15. Resource Plan

| Resource | Phases | Purpose |
| --- | --- | --- |
| AI tooling (Claude API / Claude Code) | 1–4 | PLMServer + Stargile source analysis, vault queries, documentation, development throughout |
| SME — Production Engineers | 1, 3 | ECN Track B sessions, Sprint 3 performance demo, UAT |
| SME — Engineers / Planners | 1, 3 | BOM/Supplier Track B sessions, UAT |
| SME — CBMs | 1, 3 | BOM approval workflow confirmation, UAT |
| SME — Purchasing | 1, 3 | BOM export requirements, UAT |
| SME — Document Control / QA | 1, 3, 4 | ECN compliance, RoHS/REACH, Software Validation sign-off |
| SME — SMT Engineer | 1 | ECN SMT programme dedicated session |
| Backend developer (Python) | 2–4 | FastAPI, all three modules, both adapters, Celery, PostgreSQL |
| .NET developer (movex-rest-api extensions) | 2–3 | Add MI endpoints identified in Phase 1 gap analysis — Phase 2 scoping, Phase 3 delivery |
| Frontend developer (React/TS) | 2–4 | React TypeScript UI, SM-Portal integration, WebSocket progress UI |
| IT — Windows Server / Docker | 2–4 | Docker on Windows, IIS, ADCS certificate, Movex sandbox, supplier test credentials, two-site env setup |
| Contractor (if needed) | 3 | Additional Sprint 3/4 capacity — confirmed at Phase 2 gate |
| Movex test/sandbox | 3–4 | ERP integration testing — mandatory Phase 2 gate |
| Supplier API test credentials (all 6) | 3 | Sprint 3 supplier development — mandatory Phase 2 gate |
| Knowledge Vault | 1–4 | m3-lookup, /adr, /mine, /runbook, /review, agent registry |

# 16. [PLATFORM] as Organisational AI Platform Foundation

Diagram 13 — Platform evolution roadmap: four iterations on one foundation (flowchart in Mermaid file)

| [PLATFORM] decision | Future capability enabled |
| --- | --- |
| Layered authority: Movex holds committed BOM, platform holds change history | Every future module reads change history and intelligence from the platform. Movex remains the production system of record throughout. |
| Two adapter patterns (ERP + Supplier) | Route module uses ERP Adapter. Future procurement uses Supplier Adapter. IFS adapter written once, serves all modules simultaneously for Site B. |
| Parallel async supplier processing | Performance pattern reusable for any module aggregating data from multiple external sources. |
| Shared data model across three modules | Routes, MSP, MES join the same database. No integration contracts between modules. |
| Docker on Windows Server — two-site | Deployment pattern for all future modules. Additional sites join by adding an environment file. |
| Two MAS v2.0 agent registrations | Routes, MSP, MES each add one agent. Registry grows naturally. |
| BOM comparison as first-class feature | Comparison pattern reusable for route comparison, MSP diff, and any future diffable entity. |
| movex-rest-api extension discipline (Phase 1 gap analysis) | Pattern for every future module that needs new ERP operations: map the gap in Phase 1, extend movex-rest-api in Phase 2, build against it in Phase 3. |
| SM-Portal module pattern | Every future module is a portal module. One portal, all capabilities. |

# Appendix A: Phase Timeline Summary

| Phase | Weeks | Gate Deliverables |
| --- | --- | --- |
| Phase 1 — Discovery | 1–4 | ECN Spec + BOM/Supplier Spec + All adapter interfaces + Stargile MI gap analysis + movex-rest-api extension spec + Retired lists + SM-Portal decision + Retention decisions + Two-site model + Vault entries |
| Phase 2 — Architecture | 5–6 | ADR + Shared data model + NFRs + Docker + Movex sandbox + Supplier credentials + movex-rest-api extensions scheduled + Build plan |
| Phase 3 — Build | 7–20 | 3-module platform + IFS adapter stub + Site B config + Both agents + Sprint 3 perf demo + UAT + Training materials |
| Phase 4 — Cutover | 21–24 | Go-live (both sites, both modules) + IQ/OQ/PQ + Training records + Rollback rehearsed + Both systems decommissioned + Vault handover |
| Total | 24 weeks | Stargile + PLMServer replaced · Iteration 1 live · Org AI Platform foundation established |

# Appendix B: Legacy System Summary

## Stargile — ECN (Java)

| Attribute | Detail |
| --- | --- |
| Location | Internal server — source extraction pending permission |
| Function | ECN workflow, approval routing, Movex BOM/route commit |
| ERP integration | Own Java classes calling Movex MI API directly — not movex-rest-api |
| Users | Production Engineers, Document Control, SMT Engineers, Test Engineers |
| Compliance | ISO 13485 audit trail and approval records |
| Key Phase 1 output | Complete MI program inventory + gap analysis vs movex-rest-api coverage |
| Critical gap | Status 60 exit mechanism unconfirmed — Phase 1 Track A |

## PLMServer — BOM / Supplier Intelligence (PHP/MySQL/Apache)

| Attribute | Detail |
| --- | --- |
| Location | c:/Projects/PLM/PLMServer |
| Function | BOM upload, multi-supplier pricing and availability, BOM approval for Purchasing |
| ERP integration | Movex via SQL Server read-only view (order data only — no BOM writes) |
| Users | Engineers/Planners (2 of 8 active), CBMs, Purchasing — NPS -40 |
| Status | Largely abandoned — 13-minute BOM processing, no progress feedback, SSL disabled |
| Analysis assets | analysis/PLMServer_Complete_Analysis.md + analysis/plm-tables.sql |

# Appendix C: Supplier Integration Reference

| Supplier | Auth | Rate Limit | Reliability | Key Notes |
| --- | --- | --- | --- | --- |
| DigiKey | OAuth2 | 1,000 req/day | High | Token refresh failures in PLMServer — Celery proactive refresh in platform |
| Mouser | API Key | 1,000 req/hour | High | Occasional timeouts — exponential backoff retry |
| Future Electronics | API Key | Unknown | Medium | Inconsistent response format — SupplierAdapter normalises |
| Element14 | API Key | 100 req/min | Medium | Frequent stock mismatches — staleness warning in UI |
| Verical / Arrow | API Key | Unknown | Medium |  |
| Octopart | API Key | Unknown | High | Primary source for alternative components + RoHS/REACH/WEEE compliance data |

# Appendix D: Architectural Decision Log

All decisions must be recorded in vault/decisions/ using /adr during Phase 1 and Phase 2. This log is the summary reference.

| Decision | Decision Made | Rationale |
| --- | --- | --- |
| Unified platform vs two replacements | Unified platform | Shared data model; supplier intelligence needed during ECN editing; compliance requires joined data; single ERP Adapter for both sites and both migrations. |
| Data authority model | Movex = SOT for committed production BOM; platform = change workflow and draft state | Avoids bidirectional sync risk; ISO 13485 auditor expectation; multi-site safe; AI value is in the change history and intelligence layer. |
| Stargile ERP interface | MovexRestAdapter calls movex-rest-api (HTTP); Phase 1 Track A produces MI gap analysis | One ERP boundary for the whole platform. .NET team extends movex-rest-api once. Python does not call MI directly. |
| Two-site deployment | Multi-configuration (same codebase, site-specific env files) — not multi-tenancy | Same SRX entity. Country split is deployment configuration. IFS migration is adapter swap. |
| Backend language | Python/FastAPI | AI/agent integration native; async architecture solves sequential API bottleneck; deviation from .NET standard justified by AI platform roadmap. |
| Supplier concurrency | Parallel async (asyncio) + Celery worker | 13 min → under 90 sec; Celery for background tasks without blocking API responses. |
| Database | PostgreSQL 16 | Replaces MySQL (PLMServer); removes SQL Server dependency; JSONB; ISO 13485 audit; no licence cost. |
| Deployment | Docker on Windows Server (IT has Docker familiarity) | Reproducible (IQ evidence); environment parity (OQ evidence); rollback by image tag; two-site from same images. |
| Frontend | SM-Portal module (recommended) | Shared auth, consistent UX, platform module pattern. Standalone is the documented fallback. |
| Platform name | To be decided — see Section 1 | DELTA recommended. |

# Appendix E: Project Ecosystem Map

| Project | Path | Role |
| --- | --- | --- |
| Stargile (ECN — Java) | Internal server — source pending | Replaced by ECN module. Phase 1: MI inventory + gap analysis. |
| PLMServer (BOM/Supplier — PHP) | c:/Projects/PLM/PLMServer | Replaced by BOM + Supplier modules. Full analysis available. |
| [PLATFORM] (new) | c:/Projects/[Platform]/ | Unified platform. Commit hook Sprint 1. Both agents Sprint 5. |
| movex-rest-api | c:/Projects/MOVEX/API-Integration/movex-rest-api | ERP surface. Extended in Phase 2 to cover Stargile MI gap. |
| SM-Portal | c:/Projects/SM-Portal | Frontend host candidate. Phase 1 review confirms integration. |
| Knowledge Vault | c:/Projects/Knowledge-Management | Organisational memory. Used from Phase 1 onward. |
| MyInvois-Service | c:/Projects/MyInvois-Service | Different compliance domain. Demonstrates deployment pattern. |
| WMS | c:/Projects/WMS | Future. Subscriber to bom.revised and ecn.completed events. |
| MES | Future | Iteration 4. ECN + BOM architecture is the template. |

# Appendix F: Mermaid Diagram Reference

The accompanying Markdown file (Engineering_Intelligence_Platform_Strategy_v2.md) contains all 13 diagrams in Mermaid syntax. These render interactively in GitHub, VS Code (with Mermaid extension), Notion, Confluence, or any Mermaid-compatible viewer. The diagram titles below correspond to the [DIAGRAM N] tags throughout this document.

| Diagram | Type | Section | Description |
| --- | --- | --- | --- |
| 1 | flowchart TD | Section 2 | Current state architecture — two systems, manual handoffs, pain points |
| 2 | flowchart TD | Section 3 | Layered authority model — platform manages change; Movex holds committed BOM |
| 3 | flowchart LR | Section 4 | Two-site configuration — same codebase, site-specific env files |
| 4 | sequenceDiagram | Section 4.3 | Site B IFS migration — same platform call, adapter target swapped |
| 5 | flowchart TD | Section 5 | Platform architecture overview — three modules, two adapter patterns |
| 6 | flowchart LR | Section 5.2 | ERP Adapter — corrected for Stargile's own Java MI interface |
| 7 | flowchart TD | Section 5.3 | Sequential vs parallel async supplier processing — performance comparison |
| 8 | gantt | Section 6 | 24-week programme Gantt timeline — four phases, five sprints |
| 9 | flowchart LR | Section 6.3 | Sprint sequence — five sprints across three modules |
| 10 | sequenceDiagram | Section 6.4 | Cutover sequence — two independent sequences for Stargile and PLMServer |
| 11 | stateDiagram-v2 | Section 7 | Complete ECN state machine with all status codes and transitions |
| 12 | flowchart TD | Section 9 | Two-site Docker deployment — shared images, per-site environment files |
| 13 | flowchart TD | Section 16 | Platform evolution roadmap — Iteration 1–4 on shared foundation |

[PLATFORM NAME] Engineering Intelligence Platform — Strategy v2.0 — For Management Review

Platform name to be decided — see Section 1. Replace [PLATFORM] throughout once decided.

v2.0: Corrected data authority model · Stargile MI interface · Two-site deployment · Mermaid diagrams