| Nexus Engineering Intelligence Platform Executive Summary — For Management Review | Scanfil APAC Manufacturing IT / Engineering Modernisation Strategy v2.0 March 2026 |
| --- | --- |

Context — what we are replacing and why

Scanfil APAC currently operates two independent legacy systems that manage what is fundamentally one workflow — engineering change management and product lifecycle intelligence. Stargile (Java ECN) and PLMServer (PHP BOM and supplier intelligence) share only Movex as a data layer. Neither integrates with the other. Engineers manually transfer BOM data between them.

| System | Technology | Current state | Core problem |
| --- | --- | --- | --- |
| Stargile | Java — direct Movex MI API | Running — Movex-coupled | Brittle ERP push failures · no IFS migration path · own MI interface not shared with rest of estate |
| PLMServer | PHP 7.4 / MySQL / Apache | Largely abandoned | 13+ min BOM processing · NPS −40 · HTTPS disabled · sequential API calls · no BOM versioning |

Neither system contributes to the MAS v2.0 programme. No event stream. No API surface. No structured audit data agents can act on. Every AI initiative that touches engineering change or BOM data is blocked until this is resolved.

The solution — Nexus Engineering Intelligence Platform

A unified Python/FastAPI platform replacing both systems with three tightly coupled modules — ECN, BOM, and Supplier Intelligence — built on a shared PostgreSQL data model, a Redis event bus, and two abstract adapter patterns: one for ERP systems, one for supplier APIs.

| Module | Replaces | Key architectural decision |
| --- | --- | --- |
| ECN | Stargile | ERP Adapter → movex-rest-api (.NET) → Movex. IFS adapter stub validates the interface in Sprint 4. JB Site swaps adapter config when IFS migration begins — zero platform code changes. |
| BOM | PLMServer BOM | Platform manages the change workflow and draft state. Movex remains the source of truth for committed production BOMs. Version history, BOM comparison, and optimistic locking live in the platform. |
| Supplier Intelligence | PLMServer APIManager | asyncio.gather across all parts and all suppliers concurrently. Per-supplier circuit breaker. Redis cache with 4-hour TTL. 13 minutes → under 90 seconds for a 100-part BOM. |

Three architectural clarifications confirmed for v2.0

1. Stargile's ERP interface. Stargile calls the Movex MI API directly through its own Java classes — it does not use movex-rest-api. Phase 1 Track A must produce a full MI program inventory and a gap analysis. Any MI operations Stargile uses that movex-rest-api does not yet expose become a specification of new endpoints the .NET team must add before Sprint 3. This is a new Phase 1 gate deliverable. 2. Data authority model. The v1.0 phrase 'platform owns the BOM' was imprecise. Movex remains the source of truth for committed production BOMs — MRP, production orders, and purchasing depend on it; ISO 13485 auditors expect it. The platform holds the change workflow, the draft state, the version chain, and the supplier intelligence layer. When an ECN is approved, the ERP Adapter pushes the committed revision to Movex. 3. Two-site deployment. Melbourne Site keeps Movex permanently. JB Site uses Movex now and migrates to IFS later, then splits across two countries. This is a multi-configuration deployment — same codebase, site-specific environment files — not multi-tenancy. The IFS migration is an adapter config swap. The country split is a new Docker instance from the same images. Neither requires platform code changes.

Business case — quantified from PLMServer analysis (BOM module alone)

| ~$379K quantified annual benefit | 7.3 mo estimated payback period | 65% first-year ROI | 24 wks programme duration |
| --- | --- | --- | --- |

| Benefit | Annual value | Basis |
| --- | --- | --- |
| BOM processing time savings (13 min → 90 sec) | ~$225,000 | ~3,000 engineer-hours/year at $75/hour |
| Better supplier pricing — automated best-price selection | ~$100,000 | 2% saving on $5M annual parts spend |
| Reduced BOM rework errors | ~$24,000 | 8% reduction in rework cost |
| Engineer retention — reduced frustration-driven turnover | ~$30,000 | 2 fewer replacements at $15K each |
| ECN efficiency, IFS migration risk reduction, two-site savings | Unquantified | Strategic — architecture decisions, not estimates |

All quantified figures are from the January 2025 PLMServer system analysis and apply to the BOM module alone. The ECN replacement and the Organisational AI Platform value are additive and unquantified above.

Programme — four phases, 24 weeks

| Phase | Weeks | What gets resolved |
| --- | --- | --- |
| 1 — Discovery | 1–4 | Two-system source analysis · Stargile MI inventory and movex-rest-api gap analysis · SME behavioural sessions for both systems · Three adapter interfaces defined · SM-Portal integration decision · Data retention decisions · Two-site deployment model confirmed |
| 2 — Architecture | 5–6 | Architecture Decision Record · Shared data model · movex-rest-api extensions scoped and scheduled · Movex sandbox confirmed · All six supplier API test credentials confirmed |
| 3 — Build | 7–20 | Five sprints: foundation → approval engine + BOM comparison → supplier intelligence (perf demo Sprint 3) → ERP push + IFS stub + Site B config → audit log + MAS agents + UAT |
| 4 — Cutover | 21–24 | Two independent cutover sequences (Stargile and PLMServer) · ISO 13485 Software Validation (IQ/OQ/PQ) · Training records · Both legacy systems decommissioned · Vault handover |

Hard gates before Phase 3: (1) movex-rest-api gap endpoints specified and scheduled with .NET team (2) Movex sandbox environment confirmed by IT (3) All six supplier API test credentials confirmed (4) QA-signed data retention decisions for both systems (5) Docker on Windows Server working in staging.

What this is also building — Organisational AI Platform foundation

Every decision in Nexus is a reusable pattern. The ERP Adapter pattern means the IFS migration affects one config file per site, not a platform rewrite. The Supplier Adapter means adding a new component distributor is one new class. The shared PostgreSQL data model means Routes, MSP, and MES join the same database when they are built — no integration contracts. The MAS v2.0 agent registrations mean the Knowledge Vault and every future agent can query engineering change and BOM intelligence from day one of go-live.

| Iteration | Modules added | Source systems replaced |
| --- | --- | --- |
| 1 — this programme | ECN · BOM · Supplier Intelligence | Stargile + PLMServer |
| 2 | Route Management | Stargile route module |
| 3 | MSP | New capability |
| 4 | MES | MES Modernisation Strategy v3.0 |

What I need from you before the wider stakeholder presentation

- Review the three v2.0 architectural corrections and confirm they are sound — particularly the data authority model and the two-site deployment approach

- Advise whether the IT team can confirm the hard infrastructure gates: Docker on Windows Server needs to be resolved before Phase 2 ends

- Flag any concerns about the movex-rest-api extension work — the .NET team will need to scope this in Phase 2 based on the Phase 1 MI gap analysis, this is in relation to enable more transactions within the Movex REST API

- Confirm if we need to communicate to a wider stakeholder audience so the detail level can be calibrated accordingly

Full strategy document: Engineering_Intelligence_Platform_Strategy_v2.0 (Word + Markdown with Mermaid diagrams) The Markdown file contains 13 Mermaid diagrams (architecture overview, state machine, two-site deployment, programme Gantt, cutover sequence, platform evolution roadmap, and more) that render interactively in VS Code, GitHub, or Notion.